SEVENTH FRAMEWORK PROGRAMME

Marie Curie Actions

People. International Research Staff Exchange Scheme

Full Title of the project: Possibilities and limits, challenges and obstacles of transferring CEE EU pre-accession best practices and experience to Moldova’s and Georgia's pre-accession process

Acronym: EU-PREACC

Grant Agreement Number: PIRSES-GA-2012-318911

Project period: 01.03.2013-28.02.2017

Lead partner: University of Tartu, EuroCollege

Project coordinator: Olga Bogdanova; olga.bogdnova@ut.ee; Tel: 37256656776

Contact until 28.02.2013: Margit Säre, margitsare@gmail.com

Partners:

Vilnius University

Moldova State University

Ivane Javakhishvili Tbilisi State University

Project summary

The research will cover areas of the EU-Moldova and EU-Georgia cooperation, linked to both, the European Neighbourhood Policy Action Plan and the EU conditionality. It looks at Moldova’s and Georgia's economic, legal and political situation and development. The focus of the project and project-related research is structuring the CEE states' reform experience and analysing the possibilities and limits of transferring the best practices and experience to Moldova’s and Georgia's (possible) EU pre-accession process. It analyses the situation in Moldova and Georgia and suggests benchmarking opportunities best suitable for Moldova and Georgia. The results of the analysis and researchers/lecturers exchange are wrapped up via regular thematic workshops and publications. The output of the research results is also used in improving and developing the European Union-related curricula and courses in all participating universites: in Tartu, Vilnius, Moldova and Georgia.

Work Packages

| Work package 1 | Mapping CEE states' reform experience: environment of positive conditionality – mapping of success and failure of reforms in key policy areas related to EU accession criteria (Progress Report Chapters) |
| --- | --- |

The objective of the work package 1 is to map the character and results of CEE pre-accession process from the beginning of their accession negotiations until the accession in 2004/2007. Focus will be on critical variables in reform process: which decisions and choices eventually led to faster convergence and which decisions slowed it down.

Also critical areas of harmonization and transpondation will be selected. Attention will be also given to specific circumstances of the CEE pre-accession process compared with previous practice of the EU. Work package will allow a detailed overview based on Progress Report structure and accession partnership agreement chapters. Work package should build a basis for following work packages in terms of empirical data: actual progress and Commission evaluation.

Description of work

Task 1.1: Written research and observation on Mapping CEE states' success and failure of reforms in key policy areas related to EU accession criteria

Task 1.2: Networking for building stronger bonds between the institutions and experts related to the Institutions involved in the project

Task 1.3: Lectures and seminars (knowledge dissemination) in Tblisi state university (16) and in beneficiaries universities (6)

Deliverables

D1.1. publications of research results (4) on CEE reforms and accession to the EU process, in international periodicals and in national publications in Lithuania: Politologija, Lithuanian Foreign Policy Review

D1.2. publications of research results (10) on CEE reforms and accession to the EU process in international periodicals and in Estonia: CEURUS EU-Russia Papers, EuroCollege Working Papers Series by UTARTU, Publications of the Institute of the Government and Politics of UT

D1.3. publications (6) of research results  in international periodicals and in national publications in Georgia: in Caucasus Analytical Digest, in IJTSU periodicals

D1.4.  publications of research results (6) on CEE reforms and accession to the EU process in in Moldoscopie  and Studia Universitatis, Periodical Scientific Journals by MSU

D1.5.Publication of newspaper articles/columns (4) in national media in partner countries

D1.6. Publication of podcasts (2)

D1.7. One day Workshop in Vilnius University to discuss WP progress, its deliverables and outcomes. All beneficiaries/partner are present (total appr 15 people)

D1.8. Thematic workshops (11) and lectures (10) in Vilnius University on CEE reforms and accession to the EU process. Participants: relevant Lithuanian and Georgian researchers, stakeholders

D1.9. Thematic workshops (18) and lectures (14) in University of Tartu on CEE reforms and accession to the EU process. Participants: relevant Estonian and Georgian researchers, stakeholders

D1.10. Lectures in Tbilisi State University (9 from VU, 15 UTARTU, 15 MSU)

D1.11. Seminars and networking meetings  (10) in IJTSU, with the participations of Georgian researchers , stakeholders and VU, UTARTU, MSU scholars

D1.12. Proposal of follow-up project by partner universities (2)

Staff secondments and transfer of knowledge.

Beneficiary 1 – University of Tartu - will allocate 15 secondments (person months). Out of them 10 will be allocated to experienced researchers (ER), 5 to Early Stage Researchers.

Beneficiary 2 - Vilnius University - will allocate 9 secondments (person months). Out of them 6 will be allocated to experienced researcherss (ER), 3 to Early Stage Researcher.

Beneficiary 3 – Modova University - will allocate 6 secondments (person months). Out of them 1 will be allocated to experienced researchers (ER), 5 btoEarly Stage Researchers.

Partner Tbilisi State University – will allocate 30 secondments (person months). Out of them 20 will be allocated to experienced researcher, 10 to Early Stage Researcher.

In total 60 secondments will indicatively be used in this work package

| Work package 2 | European Neighbourhood Policy and Europeanization (political, economic and legal aspects) – analysing which CEE states' pre-accession knowledge is transferable and needed |
| --- | --- |

The aim of the WP is to analyze, which part of the CEE 2004/2007 enlargement experience can be used for Moldova and Georgia, dependent on the changes in the enlargement criteria. WP 2 will also analyse the data collected and mapped and will analyse, which candidate states are the closest to Moldova and Georgia, which experience can be used for benchmarking and which reform experience can be transferred. The objective of the work package is a thorough analysis what have been the main changes in the EU enlargement criteria, set by the European Commission and which changes relate to current EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonisation. The objective is a thorough mapping of EU-Moldova and EU-Georgia cooperation in all policy fields of European Commission EU enlargement criteria – the aims set in the framework of European Neighbourhood Policy are compared with the Chapters of the Copenhagen Criteria. Among others the issues of conflict resolution, borders and de facto states will be touched upon. The WP will also construct new and enhance existing networks of international research collaborations between Member States and associated countries

Description of work

Task 2.1: Written research, observation and articles on European Neighbourhood Policy Action Plan and EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonisation

Task 2.2: Networking for building stronger bonds between the institutions and experts related to the institutions involved in the project

Task 2.3: Lectures and seminars (knowledge dissemination) on European Neighbourhood Policy Action Plan and EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonization in IJTSU; and public lectures in Moldova, Estonia and Lithuania by IJTSU  researchers, lecturers

Deliverables

D2.1. One day workshop in University of Tartu, to discuss WP progress/plans, its deliverables and outcomes (6 participants from UTARTU, IJTSU)

D2.2. publications (18) of research results on European Neighbourhood Policy Action Plan and EU-Georgia cooperation in Europeanization and harmonization in international periodicals and in national publications in Estonia: CEURUS EU-Russia Papers, EuroCollege Working Papers Series by UTARTU, Publications of the Institute of the Government and Politics of UT

D2.3. publications  (18) of research results in international periodicals and in national publications in Moldova: Periodical Scientific Journals Moldoscopie and Studia Universitatis by MSU

D2.4. publications (18) of research results in international periodicals and in national publications  in Lithuania 18: in Politologija by the Vilnius University, Lithuanian Foreign Policy Review

D2.5. publications (18) of research results in international periodicals and in national publications in Georgia: in Caucasus Analytical Digest, in IJTSU periodicals etc.

D2.6. Publication of newsletter articles (6), TV broadcasts (3), podcasts (2) on European Neighbourhood Policy and EU-Moldova and/or EU-Georgia cooperation in Europeanization

D2.7. One day Workshop in Vilnius University to discuss WP progress, its deliverables and outcomes. All beneficiaries/partner are present

D2.8. Thematic workshops (4) and lectures (6) in University of Tartu on EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonisation. Participants: relevant Estonian and Georgian researchers, stakeholders

D2.9. Thematic workshops (2) in Lithuania, 8 people from VU, IJTSU

D2.10. Thematic workshops (2) in Moldova 8 people from MSU, IJTSU

D2.11. Lectures (16 from UTARTU, 18 from MSU, 18 from VU) on European Neighbourhood Policy Action Plan and EU-Georgia cooperation in Europeanization and harmonization in Tbilisi State University

D2.12. Public Lectures (20) in Moldova, Estonia and Lithuania by Tbilisi State University researchers, lecturers

D2.13. Seminars and networking meetings (21)- on European Neighbourhood Policy Action Plan and EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonization in in Tbilisi State University

D2.14: Proposal of follow-up project by partner universities (2)

Staff secondments and transfer of knowledge

Beneficiary 1 – University of Tartu - will allocate 28 secondments (man month). Out of them 13 will be allocated to experienced researchers (ER), 13 to Early Stage Researcher (ESR) and 2 by management staff

Beneficiary 2 - Vilnius University - will allocate14 secondments. Out of them 10 will be allocated to ER, 4 to ESR .

Beneficiary 3 - Moldova University - will allocate 23 secondments. Out of them 10 will be allocated to ERs, 13 to ESRs.

Partner Tbilisi State University – will allocate 33 secondments. Out of them 10 will be allocated to ERs, 23 to ESRs.

In total 98 secondments will indicatively be used in this work package

| Work package 3 | Moldova and Georgia – the transition countries on the EU border and states between EU and Russia – analysing the specific circumstances and policy trends |
| --- | --- |

The objective of WP 3 is to analyze what is the position in Moldova’s accession and Georgia's possible pre-accession. The objective of the work package is a thorough mapping of EU-Moldova and EU-Georgia cooperation in all policy fields of European Commission EU enlargement criteria – the aims set in the framework of European Neighborhood Policy are compared to the Chapters of the Copenhagen Criteria.

The package uses the results of the work done in work packages 1 and 2 in mapping which previous candidate country and on which period of the pre-accession is most similar to Moldova’s and Georgia's situation. All Copenhagen Criteria Chapters will be looked at separately, as in different fields the comparable countries may vary. Based on the results, the analysts can suggest, which can be the most important fields where Moldova and Georgia need to focus the most to when planning policy reforms; as well as what are the steps to be made related to harmonization of legislation and public sector reforms. It also involves an analysis in which fields the CEE states’ experts monitoring is needed and would have influence and which country of origin the experts or the benchmarking data could come from.

Description of work

Task 3.1: Written research and observation on Moldova’s accession and Georgia's possible pre-accession, analysing the specific circumstances and policy trends

Task 3.2: Networking for building stronger bonds between the institutions and experts related to the institutions involved in the project

Task 3.3: Lectures and seminars (knowledge dissemination) on of EU-Moldova and EU-Georgia cooperation in all policy fields of European Commission EU enlargement criteria

Deliverables

D3.1.One day workshop in State University of Moldova to present the project and to discuss its strategy, deliverables and outcomes (participants from MSU, national scientific community, state authorities, mass media and 3 representatives from partners universities)

D3.2.Publications of research results (10) on comparative and case analysis of Moldova, Estonia, Lithuania and Georgia European transition specific circumstances and contemporary policy trends in Moldoscopie  and Studia Universitatis, Periodical Scientific Journals by MSU.

D3.3.Publications of research results (10) on comparative study of Moldova and Estonia transition pre accession strategies in CEURUS EU-Russia Papers, EuroCollege Working Papers Series by UTARTU, Publications of the Institute of the Government and Politics of UT and in Politologija by the Vilnius University

D3.4. Publications of research results (10) on comparative study of the utility of the Moldova and Lithuania transition pre accession strategies for Georgia contemporary policy in Politologija by the Vilnius University

D3.5. Publications of research results (10) on comparative study of Moldova and Georgia transition pre accession policies, strategies and perspectives in the Publications of the Tbilisi State University and Regional journals such as the Caucasus Analytical Digest

D3.6. Publication of newspaper articles (6), TV broadcasts (3) on European Neighbourhood Policy and EU-Moldova and/or EU-Georgia cooperation in Europeanization

D3.7. Lectures (at least 25) by each UTARTU,VU, MSU scholars, professors or administrators in Tbilisi State University

D3.8. Public Lectures (at least 19) in Moldova, Estonia and Lithuania by Tbilisi State University researchers, lecturers

D3.9. Participation of UTARTU,VU, MSU visiting scholars, administrators and professors in seminars and networking meetings (at least 40) on Moldova and Georgia Neighborhood Policies, European transition specific circumstances and contemporary pre-accession policy trends in Tbilisi State University

D3.10. Thematic workshops (4) in State University of Moldova on EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonization. Participants: relevant Moldovan and Georgian researchers, stakeholders

D3.11: Proposal of follow-up project by partner universities (2)

Staff secondments and transfer of knowledge

Beneficiary 1 – University of Tartu - will allocate 17 secondments. Out of them 9 will be allocated to experienced researchers (ER), 8 to Early Stage Researcher.

Beneficiary 2 – Vilnius University - will allocate 12 secondments. Out of them 9 will be allocated to experienced researchers (ER), 3 to Early Stage Researchers.

Beneficiary 3 - State University of Moldova -  will allocate 26 secondments . Out of them 11 will be allocated to experienced researchers (ER), 15 to Early Stage Researchers.

Partner Tbilisi State University – will allocate 17 secondments. Out of them 7 will be allocated to experienced researchers (ER), 10 to Early Stage Researchers.

In total 72 secondments will indicatively be used in this work package.

| Work package 4 | Teaching EU, EU-Russia relations and European Neighbourhood Policy in the context of interdisciplinary European Studies curricula |
| --- | --- |

The objective of the WP is to map the situation in Moldova’s and Georgia's education system and degree programmes. European Union-related, policy-planning and impact assessment-related curricula and courses are thoroughly analysed in the context of preparing experts for the Moldova’s public and private sector. The aim is to map the current situation and work out suggestions to curricula development or special programmes for preparing experts of policy reform, reform planning (impact analysis), negotiations to the EU and EU law and policies in general.

Description of work

Task 4.1: Written research on EU-Russia, EU-Georgia relations and European Neighbourhood Policy in the context of interdisciplinary European Studies curricula

Task 4.2: Networking for building stronger bonds between the institutions and experts related to the institutions involved in the project

Task 4.3: Lectures and seminars (knowledge dissemination) on teaching EU-Russia relations and European Neighbourhood Policy in the context of interdisciplinary European Studies curricula

Task 4.4: curricula development on teaching, for preparing experts of policy reform, reform planning, negotiations to the EU and EU law and policies.

Deliverables

D4.1. One day workshop in University of Tartu, to discuss WP progress, its deliverables and outcomes and follow up (2-3 participants from each partner)

D4.2. publications (9) of research results on EU-Russia, EU-Georgia relations and ENP in the context of interdisciplinary European Studies curricula in international periodicals and in national publications in Estonia: CEURUS EU-Russia Papers, EuroCollege Working Papers Series by UTARTU, Publications of the Institute of the Government and Politics of UT

D4.3. Publications (4) of research results in international periodicals and in national publications in Moldova: Periodical Scientific Journals Moldoscopie and Studia Universitatis by MSU

D4.4. Publications (5) of research results in international periodicals and in national publications  in Lithuania 18: in Politologija by the Vilnius University, Lithuanian Foreign Policy Review etc.

D4.5. Publications (10) of research results in international periodicals and in national publications in Georgia: in Caucasus Analytical Digest, in IJTSU periodicals etc.

D4.6. Publication of newspaper columns/articles (6), TV broadcasts (3)

D.4.7. One day thematic workshops (4) and networking meetings (14) on teaching EU-Russia relations and ENP in the context of interdisciplinary European Studies curricula in Tbilisi State University. Participants: UTARTU, VU, MSU, IJTSU researchers and relevant Georgian stakeholders

D4.8. Thematic workshops (2) in Lithuania; Participants: relevant Lithuanian and Georgian researchers, stakeholders

D4.9. Thematic workshops (2) in Moldova; Participants: relevant Moldovan and Georgian researchers, stakeholders

D4.10. Thematic workshops (2) in Estonia; Participants: relevant Estonian and Georgian researchers, stakeholders

D4.11. Lectures (minimum 12 from UTARTU, 4 from MSU, 8 from VU) on teaching EU-Russia relations and ENP in the context of interdisciplinary European Studies curricula in IJTSU

D4.12. (Public) Lectures (20) in Moldova, Estonia and Lithuania by Tbilisi State University researchers, lecturers

D4.13. Seminars and networking meetings (21)- on European Neighbourhood Policy Action Plan and EU-Moldova and/or EU-Georgia cooperation in Europeanization and harmonization in in Tbilisi State University

D4.14. Curricula development (4), for preparing experts of policy reform, reform planning, negotiations to the EU and EU law and policies.

D4.15. Proposal of follow-up project (2)

Staff secondments and transfer of knowledge

Beneficiary 1 – University of Tartu - will allocate 28 secondments. Out of them 15 will be allocated to experienced researchers (ER), 13 to  Early Stage Researchers.

Beneficiary 2 – Vilnius University - will allocate 15 secondments. Out of them 15 will be allocated to experienced researchers (ER).

Beneficiary 3 - State University of Moldova - will allocate 7 secondments (man month) and all of them will be allocated by experienced researchers (ER).

Partner Tbilisi State University – will allocate 30 secondments. Out of them 10 will be allocated to experienced researchers (ER), 20 to Early Stage Researchers.

In total 80 secondments will indicatively be used in this work package.